## Sheet1
	Restaurant Management System Charter
Project Name :		Restaurant management system

Project Manager:		Kamlesh Kshirsagar

Status:		Approved

Start and End Date:		Start Date: 23/01/2025 End Date: 27/06/2025
		Start: Jan 24 End: Sept25
Project Description:		A mobile application for ordering foodstuffs and other products from Restaurant. The app will be available on Google Play and App Store. It helps costumer’s to order foods online.

Project Team:		1.Kamlesh Kshirsagar					Project Manager

		2. Nikhil Nagawade					Sponser

		3. Omkar Mule					Team Member

		4. Satish Bhor					Team Member

		5. Abhishek Magar					Team Member

Project scope:		This project will have features like COD,UPI support, refund within the day. Food Delivery website of the company will enable it to enter the global market for serving the customers of various different countries. This will increase the sales of the meals and will help the company in growing its market sharea

Constrains:		Time:		6 months
		Budget:		25 lakh
				Prioritize Quality & budget

Benefits:		Ease of purchase for customers

		Easy Delivery

		Easy to payment

		The project encrypts all sensitive data and the purchase process is secure

Project Objective:		The Restaurant Management System helps the restaurant manager help restaurant more effectively and efficiently by computerizing meal ordering, billing and inventory control. This management system is designed for a Indian Restaurant and the interface will be in Indian.

Key Stakeholders:		Project Manager
		Project Team
		Owner
		Customers
Timeline And Key Milestone:		12 Jan : 31 Jan: Estimate the Website Cost
		2 Feb : 15 Feb Estimate time and resources
		16 Feb : 5 March Design the user interface
		6 March : 15 March building the database
		16 March : 2 Apr start building the website
		3 Apr : 16 Apr Test the website and measure performance
		17 Apr :25 Apr train employees to know how to treat with website administration
		28 April launch the website
		30 Apr Closing
Risks:		1. The team may not meet deadlines due to adding unplanned in the specification features. / 2. The team may run out of the budget due to extending development or testing time.

KAMLESH